A Sprint has 4 working days, Monday - Thursday. Friday is reserved for Sprint events (no development work). The team recorded the following work done each day.

Task Name	Initial Estimate (hours)	Date	Status / (end of day)	Time Spent Today / Work Remaining at end of day (hours)
Task 1	8	Monday	Done	8 / 0
Task 3	4	Monday	Done	8 / 0
Task 2	8	Monday	Started	8 / 8
		Tuesday	Done	6 / 0
Task 4	4	Tuesday	Done	3 / 0
Task 5	8	Wednesday	Done	6 / 0
Task 6	2	Wednesday	Done	2 / 0
Task 7	4	Wednesday	Done	3 / 0
Task 8	8	Wednesday	Started	2 / 6
		Thursday	Done	6 / 0
Task 9	2	Thursday	Done	3 / 0
Task 10	8	Thursday	Done	3 / 0
Task 11	4	Thursday	Done	3 / 0
Task 12	10	--	Not started	-
Task 13	6	--	Not started	-
Total	76

Task 2 was a complex, risky task so the team started it early. On Monday, a team member revised the time estimate to 16 hours (8 done Monday + 8 hours remaining).

1. What was the team's velocity (per day) for this Sprint? Compute velocity based on estimated times, not actual times. Show how you calculate this.

2. How many additional days would the team need to complete Tasks 12 and 13?
   Show how you compute your answer.

3. Draw a burn-down chart of this Sprint.
- Label the x- and y-axis. What do they show?
- Include a point on the graph for Day 0 (the start of work)
- Other points on the x-axis refer to status at the end of a day.