A Sprint has 4 working days, Monday - Thursday. Friday is reserved for other Sprint events (no development work). The team recorded the following work done each day.

Task Name	Estimated Time to Complete (hours)	Date Worked On	Status (Actual Time Spent) / Work Remaining at end of today
Task 1	8	Monday	done (8 hrs)
Task 8	4	Monday	done (4 hrs)
Task 2	8	Monday	in-progress (8 hrs) / 8 hours remaining
		Tuesday	done (6 hrs today)
Test 3	2	Tuesday	done (3 hrs)
Task 7	8	Wednesday	done (7 hrs)
Task 4	2	Wednesday	done (2 hrs)
Task 11	8	Wednesday	started (2 hr) / 6 hours remaining
		Thursday	done (6 hrs today)
Task 5	6	Thursday	done (6 hrs)
Task 6	4	Thursday	done (3 hrs)
Task 9	2	Thursday	done (3 hrs)
Task 10	8	Thursday	done (8 hrs)
Task 11	4	Thursday	done (6 hrs)
Task 12	12	--	not started
Task 13	4	--	not started
Total	80

Task 2 was a complex, risky task so the team started it early. On Monday, a team member revised the time estimate to 16 hours (8 done Monday + 8 remaining). The actual time spent was less than the estimate, but that is irrelevant to the burn-down chart.

1. What was the team's velocity (per day) for this Sprint? Compute velocity based on estimated times, not actual times.

2. Draw a burn-down chart of this Sprint.
- Label the tick marks on the axes
- Include a point on the graph for Day 0 (before the start of work)

3. How much additional time do you estimate will be needed to complete Tasks 12 and 13?