## Slide 1
What is a Milestone?

## Slide 2
Milestones
Indicate a project's progress toward completion.
Tangible to manager and stakeholders.
Verifiable -- its been done.
Establishes a new baseline for work products.
Frequency: ~1 per iteration

## Slide 3
Major Milestones
Inception Vision & Scope reviewed and accepted by customer and management.
Elaboration 1
a) UC1: Vote for Projects designed, implemented, tested, and reviewed.
and
b) Persistence architecture and database schema for voting designed, documented, prototype implemented, and reviewed.

## Slide 4
Milestones Provide Visibility
Software Development Team
Work Products
Customer
Manager

## Slide 5
Steve McConnell suggests...
Use Binary Milestones
(100% Done or Not Done)
Avoid fuzzy, mushy milestones
A Milestone is either "100% done" or "100% not done."
Allowing a little step from "100% done" to "90% done" has historically been found to reduce the quality of the status information from "very good" to "awful."

## Slide 6
Other Goals
These probably don't qualify as Milestones:
Logging framework selected, convention for logging levels documented, and implemented in code.
Configuration Management plan documented and explained to team.
  Includes what to put in CM, what not to put in CM, directory layout, criteria for submitting work.
Coding and documentation standard documented and explained to team. (PPQA responsible)

## Slide 7
Minor Milestones
Purpose: keep the project on track.
Track a project's progress.
Tangible to team and manager.
Verifiable -- its been done.